## Data
Project | Fleet | Phase | Task | Duration | StartDate | EndDate | Color | Vendor
777-200 | 772 | EIS Release | ITCM | 4 | 2016-01-04 | 2016-01-08 |  | Panasonic
777-200 | 772 | EIS Release | Workshop # 1 | 4 | 2016-01-11 | 2016-01-15 |  | Panasonic
777-200 | 772 | EIS Release | Workshop # 2 | 4 | 2016-01-18 | 2016-01-22 |  | Panasonic
777-200 | 772 | EIS Release | Workshop # N | 4 | 2016-01-25 | 2016-01-29 |  | Panasonic
777-200 | 772 | EIS Release | CDR / Software Req Freeze | 4 | 2016-02-08 | 2016-02-12 |  | Panasonic
777-200 | 772 | EIS Release | EOI Demo 1 | 4 | 2016-02-15 | 2016-02-19 |  | Panasonic
777-200 | 772 | EIS Release | EOI Demo 2 | 4 | 2016-02-22 | 2016-02-26 |  | Panasonic
777-200 | 772 | EIS Release | EOI Demo 3 | 4 | 2016-03-07 | 2016-03-11 |  | Panasonic
777-200 | 772 | EIS Release | EOI Demo 4 | 4 | 2016-03-14 | 2016-03-18 |  | Panasonic
777-200 | 772 | EIS Release | Cust Dry Run (IFE) | 4 | 2016-03-21 | 2016-03-25 |  | Panasonic
777-200 | 772 | EIS Release | Cust Dry Run (IFC) | 4 | 2016-04-04 | 2016-04-08 |  | Panasonic
777-200 | 772 | EIS Release | FSAT/CATP (IFE) | 4 | 2016-04-11 | 2016-04-15 |  | Panasonic
777-200 | 772 | EIS Release | FSAT/CATP (IFC) | 4 | 2016-04-18 | 2016-04-22 |  | Panasonic
777-200 | 772 | EIS Release | FSAT/CATP 2 (IFE) | 4 | 2016-04-25 | 2016-04-29 |  | Panasonic
777-200 | 772 | EIS Release | FSAT/CATP 2 (IFC) | 4 | 2016-05-09 | 2016-05-13 |  | Panasonic
777-200 | 772 | EIS Release | SW ODD Baseline | 4 | 2016-05-16 | 2016-05-20 |  | Panasonic
777-200 | 772 | EIS Release | SW ODD | 4 | 2016-05-23 | 2016-05-27 |  | Panasonic
777-200 | 772 | EIS Release | SW Install | 4 | 2016-06-06 | 2016-06-10 |  | Panasonic
777-200 | 772 | EIS Release | Ground Check | 4 | 2016-06-13 | 2016-06-17 |  | Panasonic
777-200 | 772 | EIS Release | Functional Check Flt(s) | 4 | 2016-06-20 | 2016-06-24 | red | Panasonic
777-200 | 772 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Panasonic
777-300 | 773 | EIS Release | ITCM | 4 | 2016-01-04 | 2016-01-08 |  | Panasonic
777-300 | 773 | EIS Release | Workshop # 1 | 4 | 2016-01-11 | 2016-01-15 |  | Panasonic
777-300 | 773 | EIS Release | Workshop # 2 | 4 | 2016-01-18 | 2016-01-22 |  | Panasonic
777-300 | 773 | EIS Release | Workshop # N | 4 | 2016-01-25 | 2016-01-29 |  | Panasonic
777-300 | 773 | EIS Release | CDR / Software Req Freeze | 4 | 2016-02-08 | 2016-02-12 |  | Panasonic
777-300 | 773 | EIS Release | EOI Demo 1 | 4 | 2016-02-15 | 2016-02-19 |  | Panasonic
777-300 | 773 | EIS Release | EOI Demo 2 | 4 | 2016-02-22 | 2016-02-26 |  | Panasonic
777-300 | 773 | EIS Release | EOI Demo 3 | 4 | 2016-03-07 | 2016-03-11 |  | Panasonic
777-300 | 773 | EIS Release | EOI Demo 4 | 4 | 2016-03-14 | 2016-03-18 |  | Panasonic
777-300 | 773 | EIS Release | Cust Dry Run (IFE) | 4 | 2016-03-21 | 2016-03-25 |  | Panasonic
777-300 | 773 | EIS Release | Cust Dry Run (IFC) | 4 | 2016-04-04 | 2016-04-08 |  | Panasonic
777-300 | 773 | EIS Release | FSAT/CATP (IFE) | 4 | 2016-04-11 | 2016-04-15 |  | Panasonic
777-300 | 773 | EIS Release | FSAT/CATP (IFC) | 4 | 2016-04-18 | 2016-04-22 |  | Panasonic
777-300 | 773 | EIS Release | FSAT/CATP 2 (IFE) | 4 | 2016-04-25 | 2016-04-29 |  | Panasonic
777-300 | 773 | EIS Release | FSAT/CATP 2 (IFC) | 4 | 2016-05-09 | 2016-05-13 |  | Panasonic
777-300 | 773 | EIS Release | SW ODD Baseline | 4 | 2016-05-16 | 2016-05-20 |  | Panasonic
777-300 | 773 | EIS Release | SW ODD | 4 | 2016-05-23 | 2016-05-27 |  | Panasonic
777-300 | 773 | EIS Release | SW Install | 4 | 2016-06-06 | 2016-06-10 |  | Panasonic
777-300 | 773 | EIS Release | Ground Check | 4 | 2016-06-13 | 2016-06-17 |  | Panasonic
777-300 | 773 | EIS Release | Functional Check Flt(s) | 4 | 2016-06-20 | 2016-06-24
777-300 | 773 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Panasonic
787-800 | 787 | EIS Release | ITCM | 4 | 2016-01-04 | 2016-01-08 |  | Panasonic
787-800 | 787 | EIS Release | Workshop # 1 | 4 | 2016-01-11 | 2016-01-15 |  | Panasonic
787-800 | 787 | EIS Release | Workshop # 2 | 4 | 2016-01-18 | 2016-01-22 |  | Panasonic
787-800 | 787 | EIS Release | Workshop # N | 4 | 2016-01-25 | 2016-01-29 |  | Panasonic
787-800 | 787 | EIS Release | CDR / Software Req Freeze | 4 | 2016-02-08 | 2016-02-12 |  | Panasonic
787-800 | 787 | EIS Release | EOI Demo 1 | 4 | 2016-02-15 | 2016-02-19 |  | Panasonic
787-800 | 787 | EIS Release | EOI Demo 2 | 4 | 2016-02-22 | 2016-02-26 |  | Panasonic
787-800 | 787 | EIS Release | EOI Demo 3 | 4 | 2016-03-07 | 2016-03-11 |  | Panasonic
787-800 | 787 | EIS Release | EOI Demo 4 | 4 | 2016-03-14 | 2016-03-18 |  | Panasonic
787-800 | 787 | EIS Release | Cust Dry Run (IFE) | 4 | 2016-03-21 | 2016-03-25 |  | Panasonic
787-800 | 787 | EIS Release | Cust Dry Run (IFC) | 4 | 2016-04-04 | 2016-04-08 |  | Panasonic
787-800 | 787 | EIS Release | FSAT/CATP (IFE) | 4 | 2016-04-11 | 2016-04-15 |  | Panasonic
787-800 | 787 | EIS Release | FSAT/CATP (IFC) | 4 | 2016-04-18 | 2016-04-22 |  | Panasonic
787-800 | 787 | EIS Release | FSAT/CATP 2 (IFE) | 4 | 2016-04-25 | 2016-04-29 |  | Panasonic
787-800 | 787 | EIS Release | FSAT/CATP 2 (IFC) | 4 | 2016-05-09 | 2016-05-13 |  | Panasonic
787-800 | 787 | EIS Release | SW ODD Baseline | 4 | 2016-05-16 | 2016-05-20 |  | Panasonic
787-800 | 787 | EIS Release | SW ODD | 4 | 2016-05-23 | 2016-05-27 |  | Panasonic
787-800 | 787 | EIS Release | SW Install | 4 | 2016-06-06 | 2016-06-10 |  | Panasonic
787-800 | 787 | EIS Release | Ground Check | 4 | 2016-06-13 | 2016-06-17 |  | Panasonic
787-800 | 787 | EIS Release | Functional Check Flt(s) | 4 | 2016-06-20 | 2016-06-24
787-800 | 787 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Panasonic
B737…. | 737 | EIS Release | ITCM | 4 | 2016-01-04 | 2016-01-08 |  | Thales
B737…. | 737 | EIS Release | Workshop # 1 | 4 | 2016-01-11 | 2016-01-15 |  | Thales
B737…. | 737 | EIS Release | Workshop # 2 | 4 | 2016-01-18 | 2016-01-22 |  | Thales
B737…. | 737 | EIS Release | Workshop # N | 4 | 2016-01-25 | 2016-01-29 |  | Thales
B737…. | 737 | EIS Release | CDR / Software Req Freeze | 4 | 2016-02-08 | 2016-02-12 |  | Thales
B737…. | 737 | EIS Release | EOI Demo 1 | 4 | 2016-02-15 | 2016-02-19 |  | Thales
B737…. | 737 | EIS Release | EOI Demo 2 | 4 | 2016-02-22 | 2016-02-26 |  | Thales
B737…. | 737 | EIS Release | EOI Demo 3 | 4 | 2016-03-07 | 2016-03-11 |  | Thales
B737…. | 737 | EIS Release | EOI Demo 4 | 4 | 2016-03-14 | 2016-03-18 |  | Thales
B737…. | 737 | EIS Release | Cust Dry Run (IFE) | 4 | 2016-03-21 | 2016-03-25 |  | Thales
B737…. | 737 | EIS Release | Cust Dry Run (IFC) | 4 | 2016-04-04 | 2016-04-08 |  | Thales
B737…. | 737 | EIS Release | FSAT/CATP (IFE) | 4 | 2016-04-11 | 2016-04-15 |  | Thales
B737…. | 737 | EIS Release | FSAT/CATP (IFC) | 4 | 2016-04-18 | 2016-04-22 |  | Thales
B737…. | 737 | EIS Release | FSAT/CATP 2 (IFE) | 4 | 2016-04-25 | 2016-04-29 |  | Thales
B737…. | 737 | EIS Release | FSAT/CATP 2 (IFC) | 4 | 2016-05-09 | 2016-05-13 |  | Thales
B737…. | 737 | EIS Release | SW ODD Baseline | 4 | 2016-05-16 | 2016-05-20 |  | Thales
B737…. | 737 | EIS Release | SW ODD | 4 | 2016-05-23 | 2016-05-27 |  | Thales
B737…. | 737 | EIS Release | SW Install | 4 | 2016-06-06 | 2016-06-10 |  | Thales
B737…. | 737 | EIS Release | Ground Check | 4 | 2016-06-13 | 2016-06-17 |  | Thales
B737…. | 737 | EIS Release | Functional Check Flt(s) | 4 | 2016-06-20 | 2016-06-24 |  | Thales
B737…. | 737 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Thales
A319…. | A319 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Thales
A319…. | A319 | EIS Release | ITCM | 4 | 2016-01-04 | 2016-01-08 |  | Thales
A319…. | A319 | EIS Release | Workshop # 1 | 4 | 2016-01-11 | 2016-01-15 |  | Thales
A319…. | A319 | EIS Release | Workshop # 2 | 4 | 2016-01-18 | 2016-01-22 |  | Thales
A319…. | A319 | EIS Release | Workshop # N | 4 | 2016-01-25 | 2016-01-29 |  | Thales
A319…. | A319 | EIS Release | CDR / Software Req Freeze | 4 | 2016-02-08 | 2016-02-12 |  | Thales
A319…. | A319 | EIS Release | EOI Demo 1 | 4 | 2016-02-15 | 2016-02-19 |  | Thales
A319…. | A319 | EIS Release | EOI Demo 2 | 4 | 2016-02-22 | 2016-02-26 |  | Thales
A319…. | A319 | EIS Release | EOI Demo 3 | 4 | 2016-03-07 | 2016-03-11 |  | Thales
A319…. | A319 | EIS Release | EOI Demo 4 | 4 | 2016-03-14 | 2016-03-18 |  | Thales
A319…. | A319 | EIS Release | Cust Dry Run (IFE) | 4 | 2016-03-21 | 2016-03-25 |  | Thales
A319…. | A319 | EIS Release | Cust Dry Run (IFC) | 4 | 2016-04-04 | 2016-04-08 |  | Thales
A319…. | A319 | EIS Release | FSAT/CATP (IFE) | 4 | 2016-04-11 | 2016-04-15 |  | Thales
A319…. | A319 | EIS Release | FSAT/CATP (IFC) | 4 | 2016-04-18 | 2016-04-22 |  | Thales
A319…. | A319 | EIS Release | FSAT/CATP 2 (IFE) | 4 | 2016-04-25 | 2016-04-29 |  | Thales
A319…. | A319 | EIS Release | FSAT/CATP 2 (IFC) | 4 | 2016-05-09 | 2016-05-13 |  | Thales
A319…. | A319 | EIS Release | SW ODD Baseline | 4 | 2016-05-16 | 2016-05-20 |  | Thales
A319…. | A319 | EIS Release | SW ODD | 4 | 2016-05-23 | 2016-05-27 |  | Thales
A319…. | A319 | EIS Release | SW Install | 4 | 2016-06-06 | 2016-06-10 |  | Thales
A319…. | A319 | EIS Release | Ground Check | 4 | 2016-06-13 | 2016-06-17 |  | Thales
A319…. | A319 | EIS Release | Functional Check Flt(s) | 4 | 2016-06-20 | 2016-06-24 |  | Thales
A319…. | A319 | EIS Release | Prototype Eval Period | 4 | 2016-07-04 | 2016-07-08 |  | Thales

## ColorCodes
Task | Color
RFP through Contract Award | #D8E4BC
ITCM | #76933C
Workshop # 1 | #948A54
Workshop # 2 | #948A54
Workshop # N | #948A54
CDR / Software Req Freeze | #494529
EOI Demo 1 | #E6B8B7
EOI Demo 2 | #E6B8B7
EOI Demo 3 | #E6B8B7
EOI Demo 4 | #E6B8B7
Cust Dry Run (IFE) | #963634
Cust Dry Run (IFC) | #963634
FSAT/CATP (IFE) | #FF0000
FSAT/CATP (IFC) | #FF0000
FSAT/CATP 2 (IFE) | #C00000
FSAT/CATP 2 (IFC) | #C00000
SW ODD Baseline | #CCC0DA
SW ODD | #B1A0C7
SW Install | #60497A
Ground Check | #92CDDC
Functional Check Flt(s) | #31869B
Prototype Eval Period | #215967