## Data
Project | Fleet | Phase | Task | Duration | StartDate | EndDate | Color | Vendor
777-200 |  | EIS Release | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Panasonic
777-200 |  | EIS Release | ITCM | 5 | 2016-01-04 | 2016-01-08 |  | Panasonic
777-200 |  | EIS Release | Workshops | 5 | 2016-01-11 | 2016-01-15 |  | Panasonic
777-200 |  | EIS Release | Workshops | 5 | 2016-01-18 | 2016-01-22 |  | Panasonic
777-200 |  | EIS Release | Workshops | 5 | 2016-01-25 | 2016-01-29 |  | Panasonic
777-200 |  | EIS Release | CDR/Software Req Freeze | 5 | 2016-02-08 | 2016-02-12 |  | Panasonic
777-200 |  | EIS Release | EOI Demos | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | EOI Demos | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | EOI Demos | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | EOI Demos | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | Cust Dry Run (IFE) | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | Cust Dry Run (IFC) | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | FSAT/CATP (IFE) | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | FSAT/CATP (IFC) | 1 |  |  |  | Panasonic
777-200 |  | EIS Release | SW ODD Baseline | 5 | 2016-05-16 | 2016-05-20 |  | Panasonic
777-200 |  | EIS Release | SW ODD | 5 | 2016-05-23 | 2016-05-27 |  | Panasonic
777-200 |  | EIS Release | SW Install | 5 | 2016-06-06 | 2016-06-10 |  | Panasonic
777-200 |  | EIS Release | Ground Check | 5 | 2016-01-04 | 2016-01-08 |  | Panasonic
777-200 |  | EIS Release | Functional Check Flt(s) | 5 | 2016-06-20 | 2016-06-24 |  | Panasonic
777-200 |  | EIS Release | Prototype Eval Period | 5 | 2016-07-04 | 2016-07-08 |  | Panasonic
777-200 |  | EIS Release | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Panasonic
777-200 |  | EIS Release-2 | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Panasonic
777-200 |  | EIS Release-2 | ITCM | 5 | 2016-02-01 | 2016-02-05 |  | Panasonic
777-200 |  | EIS Release-2 | Workshops | 5 | 2016-02-08 | 2016-02-12 |  | Panasonic
777-200 |  | EIS Release-2 | Workshops | 5 | 2016-02-15 | 2016-02-19 |  | Panasonic
777-200 |  | EIS Release-2 | Workshops | 5 | 2016-02-22 | 2016-02-26 |  | Panasonic
777-200 |  | EIS Release-2 | CDR/Software Req Freeze | 5 | 2016-03-07 | 2016-03-11 |  | Panasonic
777-200 |  | EIS Release-2 | EOI Demos | 5 | 2016-03-14 | 2016-03-18 |  | Panasonic
777-200 |  | EIS Release-2 | EOI Demos | 5 | 2016-03-21 | 2016-03-25 |  | Panasonic
777-200 |  | EIS Release-2 | EOI Demos | 5 | 2016-04-04 | 2016-04-08 |  | Panasonic
777-200 |  | EIS Release-2 | EOI Demos | 5 | 2016-04-11 | 2016-04-15 |  | Panasonic
777-200 |  | EIS Release-2 | Cust Dry Run (IFE) | 5 | 2016-04-18 | 2016-04-22 |  | Panasonic
777-200 |  | EIS Release-2 | Cust Dry Run (IFC) | 5 | 2016-05-02 | 2016-05-06 |  | Panasonic
777-200 |  | EIS Release-2 | FSAT/CATP (IFE) | 5 | 2016-05-09 | 2016-05-13 |  | Panasonic
777-200 |  | EIS Release-2 | FSAT/CATP (IFC) | 5 | 2016-05-16 | 2016-05-20 |  | Panasonic
777-200 |  | EIS Release-2 | SW ODD Baseline | 5 | 2016-06-13 | 2016-06-17 |  | Panasonic
777-200 |  | EIS Release-2 | SW ODD | 5 | 2016-06-20 | 2016-06-24 |  | Panasonic
777-200 |  | EIS Release-2 | SW Install | 5 | 2016-07-04 | 2016-07-08 |  | Panasonic
777-200 |  | EIS Release-2 | Ground Check | 5 | 2016-07-11 | 2016-07-15 |  | Panasonic
777-200 |  | EIS Release-2 | Functional Check Flt(s) | 5 | 2016-07-18 | 2016-07-22 |  | Panasonic
777-200 |  | EIS Release-2 | Prototype Eval Period | 5 | 2016-08-01 | 2016-08-05 |  | Panasonic
777-200 |  | EIS Release-2 | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Panasonic
777-300 |  | EIS Release | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Panasonic
777-300 |  | EIS Release | ITCM | 5 | 2016-01-04 | 2016-01-08 |  | Panasonic
777-300 |  | EIS Release | Workshops | 5 | 2016-01-11 | 2016-01-15 |  | Panasonic
777-300 |  | EIS Release | Workshops | 5 | 2016-01-18 | 2016-01-22 |  | Panasonic
777-300 |  | EIS Release | Workshops | 5 | 2016-01-25 | 2016-01-29 |  | Panasonic
777-300 |  | EIS Release | CDR/Software Req Freeze | 4 | 2016-02-09 | 2016-02-12 |  | Panasonic
777-300 |  | EIS Release | EOI Demos | 5 | 2016-02-15 | 2016-02-19 |  | Panasonic
777-300 |  | EIS Release | EOI Demos | 5 | 2016-02-22 | 2016-02-26 |  | Panasonic
777-300 |  | EIS Release | EOI Demos | 5 | 2016-03-07 | 2016-03-11 |  | Panasonic
777-300 |  | EIS Release | EOI Demos | 5 | 2016-03-14 | 2016-03-18 |  | Panasonic
777-300 |  | EIS Release | Cust Dry Run (IFE) | 5 | 2016-03-21 | 2016-03-25 |  | Panasonic
777-300 |  | EIS Release | Cust Dry Run (IFC) | 5 | 2016-04-04 | 2016-04-08 |  | Panasonic
777-300 |  | EIS Release | FSAT/CATP (IFE) | 5 | 2016-04-11 | 2016-04-15 |  | Panasonic
777-300 |  | EIS Release | FSAT/CATP (IFC) | 5 | 2016-04-18 | 2016-04-22 |  | Panasonic
777-300 |  | EIS Release | SW ODD Baseline | 5 | 2016-05-16 | 2016-05-20 |  | Panasonic
777-300 |  | EIS Release | SW ODD | 5 | 2016-05-23 | 2016-05-27 |  | Panasonic
777-300 |  | EIS Release | SW Install | 5 | 2016-06-06 | 2016-06-10 |  | Panasonic
777-300 |  | EIS Release | Ground Check | 5 | 2016-06-13 | 2016-06-17 |  | Panasonic
777-300 |  | EIS Release | Functional Check Flt(s) | 5 | 2016-06-20 | 2016-06-24 |  | Panasonic
777-300 |  | EIS Release | Prototype Eval Period | 5 | 2016-07-04 | 2016-07-08 |  | Panasonic
777-300 |  | EIS Release | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Panasonic
787-800 |  | EIS Release | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Panasonic
787-800 |  | EIS Release | ITCM | 5 | 2016-01-04 | 2016-01-08 |  | Panasonic
787-800 |  | EIS Release | Workshops | 5 | 2016-01-11 | 2016-01-15 |  | Panasonic
787-800 |  | EIS Release | Workshops | 5 | 2016-01-18 | 2016-01-22 |  | Panasonic
787-800 |  | EIS Release | Workshops | 5 | 2016-01-25 | 2016-01-29 |  | Panasonic
787-800 |  | EIS Release | CDR/Software Req Freeze | 4 | 2016-02-09 | 2016-02-12 |  | Panasonic
787-800 |  | EIS Release | EOI Demos | 5 | 2016-02-15 | 2016-02-19 |  | Panasonic
787-800 |  | EIS Release | EOI Demos | 5 | 2016-02-22 | 2016-02-26 |  | Panasonic
787-800 |  | EIS Release | EOI Demos | 5 | 2016-03-07 | 2016-03-11 |  | Panasonic
787-800 |  | EIS Release | EOI Demos | 5 | 2016-03-14 | 2016-03-18 |  | Panasonic
787-800 |  | EIS Release | Cust Dry Run (IFE) | 5 | 2016-03-21 | 2016-03-25 |  | Panasonic
787-800 |  | EIS Release | Cust Dry Run (IFC) | 5 | 2016-04-04 | 2016-04-08 |  | Panasonic
787-800 |  | EIS Release | FSAT/CATP (IFE) | 5 | 2016-04-11 | 2016-04-15 |  | Panasonic
787-800 |  | EIS Release | FSAT/CATP (IFC) | 5 | 2016-04-18 | 2016-04-22 |  | Panasonic
787-800 |  | EIS Release | SW ODD Baseline | 5 | 2016-05-16 | 2016-05-20 |  | Panasonic
787-800 |  | EIS Release | SW ODD | 5 | 2016-05-23 | 2016-05-27 |  | Panasonic
787-800 |  | EIS Release | SW Install | 5 | 2016-06-06 | 2016-06-10 |  | Panasonic
787-800 |  | EIS Release | Ground Check | 5 | 2016-06-13 | 2016-06-17 |  | Panasonic
787-800 |  | EIS Release | Functional Check Flt(s) | 5 | 2016-06-20 | 2016-06-24 |  | Panasonic
787-800 |  | EIS Release | Prototype Eval Period | 5 | 2016-07-04 | 2016-07-08 |  | Panasonic
787-800 |  | EIS Release | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Panasonic
B737…. |  | EIS Release | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Thales
B737…. |  | EIS Release | ITCM | 5 | 2016-01-04 | 2016-01-08 |  | Thales
B737…. |  | EIS Release | Workshops | 5 | 2016-01-11 | 2016-01-15 |  | Thales
B737…. |  | EIS Release | Workshops | 5 | 2016-01-18 | 2016-01-22 |  | Thales
B737…. |  | EIS Release | Workshops | 5 | 2016-01-25 | 2016-01-29 |  | Thales
B737…. |  | EIS Release | CDR/Software Req Freeze | 4 | 2016-02-09 | 2016-02-12 |  | Thales
B737…. |  | EIS Release | EOI Demos | 5 | 2016-02-15 | 2016-02-19 |  | Thales
B737…. |  | EIS Release | EOI Demos | 5 | 2016-02-22 | 2016-02-26 |  | Thales
B737…. |  | EIS Release | EOI Demos | 5 | 2016-03-07 | 2016-03-11 |  | Thales
B737…. |  | EIS Release | EOI Demos | 5 | 2016-03-14 | 2016-03-18 |  | Thales
B737…. |  | EIS Release | Cust Dry Run (IFE) | 5 | 2016-03-21 | 2016-03-25 |  | Thales
B737…. |  | EIS Release | Cust Dry Run (IFC) | 5 | 2016-04-04 | 2016-04-08 |  | Thales
B737…. |  | EIS Release | FSAT/CATP (IFE) | 5 | 2016-04-11 | 2016-04-15 |  | Thales
B737…. |  | EIS Release | FSAT/CATP (IFC) | 5 | 2016-04-18 | 2016-04-22 |  | Thales
B737…. |  | EIS Release | SW ODD Baseline | 5 | 2016-05-16 | 2016-05-20 |  | Thales
B737…. |  | EIS Release | SW ODD | 5 | 2016-05-23 | 2016-05-27 |  | Thales
B737…. |  | EIS Release | SW Install | 5 | 2016-06-06 | 2016-06-10 |  | Thales
B737…. |  | EIS Release | Ground Check | 5 | 2016-06-13 | 2016-06-17 |  | Thales
B737…. |  | EIS Release | Functional Check Flt(s) | 5 | 2016-06-20 | 2016-06-24 |  | Thales
B737…. |  | EIS Release | Prototype Eval Period | 5 | 2016-07-04 | 2016-07-08 |  | Thales
B737…. |  | EIS Release | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Thales
A319…. |  | EIS Release | Timeline | 5 | 2015-12-26 | 2015-12-31 |  | Thales
A319…. |  | EIS Release | ITCM | 5 | 2016-01-04 | 2016-01-08 |  | Thales
A319…. |  | EIS Release | Workshops | 5 | 2016-01-11 | 2016-01-15 |  | Thales
A319…. |  | EIS Release | Workshops | 5 | 2016-01-18 | 2016-01-22 |  | Thales
A319…. |  | EIS Release | Workshops | 5 | 2016-01-25 | 2016-01-29 |  | Thales
A319…. |  | EIS Release | CDR/Software Req Freeze | 4 | 2016-02-09 | 2016-02-12 |  | Thales
A319…. |  | EIS Release | EOI Demos | 5 | 2016-02-15 | 2016-02-19 |  | Thales
A319…. |  | EIS Release | EOI Demos | 5 | 2016-02-22 | 2016-02-26 |  | Thales
A319…. |  | EIS Release | EOI Demos | 5 | 2016-03-07 | 2016-03-11 |  | Thales
A319…. |  | EIS Release | EOI Demos | 5 | 2016-03-14 | 2016-03-18 |  | Thales
A319…. |  | EIS Release | Cust Dry Run (IFE) | 5 | 2016-03-21 | 2016-03-25 |  | Thales
A319…. |  | EIS Release | Cust Dry Run (IFC) | 5 | 2016-04-04 | 2016-04-08 |  | Thales
A319…. |  | EIS Release | FSAT/CATP (IFE) | 5 | 2016-04-11 | 2016-04-15 |  | Thales
A319…. |  | EIS Release | FSAT/CATP (IFC) | 5 | 2016-04-18 | 2016-04-22 |  | Thales
A319…. |  | EIS Release | SW ODD Baseline | 5 | 2016-05-16 | 2016-05-20 |  | Thales
A319…. |  | EIS Release | SW ODD | 5 | 2016-05-23 | 2016-05-27 |  | Thales
A319…. |  | EIS Release | SW Install | 5 | 2016-06-06 | 2016-06-10 |  | Thales
A319…. |  | EIS Release | Ground Check | 5 | 2016-06-13 | 2016-06-17 |  | Thales
A319…. |  | EIS Release | Functional Check Flt(s) | 5 | 2016-06-20 | 2016-06-24 |  | Thales
A319…. |  | EIS Release | Prototype Eval Period | 5 | 2016-07-04 | 2016-07-08 |  | Thales
A319…. |  | EIS Release | Timeline | 2 | 2017-01-01 | 2017-01-03 |  | Thales

## ColorCodes
Task | Color
RFP through Contract Award | #D8E4BC
CDR/Software Req Freeze | #494529
Cust Dry Run (IFC) | #963634
SW ODD Baseline | #CCC0DA
Ground Check | #92CDDC
Prototype Eval Period | #215967
ITCM | #76933C
EOI Demos | #E6B8B7
FSAT/CATP (IFE) | #FF0000
SW ODD | #B1A0C7
Functional Check Flt(s) | #31869B
Timeline | transparent
Workshops | #948A54
Cust Dry Run (IFE) | #963634
FSAT/CATP (IFE) | #FF0000
FSAT/CATP (IFC) | #FF0000
SW Install | #60497A