## Sheet1
Project | Phase | Task | Duration | StartDate | EndDate
777-200 | eXTV Release | CDR / Software Req Freeze
777-200 | eXTV Release | End of Iteration Demo 1
777-200 | eXTV Release | End of Iteration Demo 2
777-200 | eXTV Release | End of Iteration Demo 3
777-200 | eXTV Release | End of Iteration Demo 4
777-200 | eXTV Release | Customer Dry Run (IFE) | 5 | 2015-06-15 | 2015-06-19
777-200 | eXTV Release | Customer Dry Run (IFC)
777-200 | eXTV Release | Bug Fix | 5 | 2015-06-22 | 2015-06-26
777-200 | eXTV Release | ALST/FE Dry Run | 10 | 2015-06-29 | 2015-07-10
777-200 | eXTV Release | Bug Fix | 5 | 2015-07-13 | 2015-07-17
777-200 | eXTV Release | FSAT/Customer ATP (IFE) | 7 | 2015-07-20 | 2015-07-28
777-200 | eXTV Release | FSAT/Customer ATP (IFC)
777-200 | eXTV Release | SQA | 5 | 2015-08-01 | 2015-08-26
777-200 | eXTV Release | SW ODD | 1 | 2015-09-02 | 2015-09-02
777-200 | eXTV Release | SW Install
777-200 | eXTV Release | Ground Check
777-200 | eXTV Release | Functional Check Flight(s)
777-200 | eXTV Release | Fly Along Support
777-200 | eXTV Release | Post Implementation Follow Up
777-200 | PAC WISP Release | Customer Dry Run (IFE) | 5 | 2015-10-05 | 2015-10-09
777-200 | PAC WISP Release | Customer Dry Run (IFC) | 5 | 2015-10-12 | 2015-10-16
777-200 | PAC WISP Release | Bug Fix | 5 | 2015-10-19 | 2015-10-23
777-200 | PAC WISP Release | ALST/FE Dry Run | 10 | 2015-10-26 | 2015-11-06
777-200 | PAC WISP Release | Bug Fix | 5 | 2015-11-09 | 2015-11-13
777-200 | PAC WISP Release | FSAT/Customer ATP (IFE) | 5 | 2015-11-30 | 2015-12-04
777-200 | PAC WISP Release | FSAT/Customer ATP (IFC) | 5 | 2015-07-12 | 2015-12-11
777-200 | PAC WISP Release | SQA | 5 | 2016-01-04 | 2016-01-08
777-200 | PAC WISP Release | SW ODD | 1 | 2016-01-15 | 2016-01-15
777-200 | PAC WISP Release | SW Install
777-200 | PAC WISP Release | Ground Check
777-200 | PAC WISP Release | Functional Check Flight(s)
777-200 | PAC WISP Release | Fly Along Support
777-200 | PAC WISP Release | Post Implementation Follow Up
777-200 | Phase 2.4 Release | CDR / Software Req Freeze
777-200 | Phase 2.4 Release | End of Iteration Demo 1
777-200 | Phase 2.4 Release | End of Iteration Demo 2
777-200 | Phase 2.4 Release | End of Iteration Demo 3
777-200 | Phase 2.4 Release | End of Iteration Demo 4
777-200 | Phase 2.4 Release | Customer Dry Run (IFE) | 5 | 2016-04-25 | 2016-04-29
777-200 | Phase 2.4 Release | Customer Dry Run (IFC) | 5 | 2016-05-02 | 2016-05-06
777-200 | Phase 2.4 Release | Bug Fix | 10 | 2016-05-09 | 2016-05-20
777-200 | Phase 2.4 Release | ALST/FE Dry Run | 10 | 2016-05-23 | 2016-06-03
777-200 | Phase 2.4 Release | Bug Fix | 5 | 2016-06-06 | 2016-06-10
777-200 | Phase 2.4 Release | FSAT/Customer ATP (IFE) | 5 | 2016-06-13 | 2016-06-17
777-200 | Phase 2.4 Release | FSAT/Customer ATP (IFC) | 5 | 2016-06-20 | 2016-06-24
777-200 | Phase 2.4 Release | SQA | 7 | 2016-07-07 | 2016-07-15
777-200 | Phase 2.4 Release | SW ODD | 1 | 2016-07-29 | 2016-07-29
777-200 | Phase 2.4 Release | SW Install
777-200 | Phase 2.4 Release | Ground Check
777-200 | Phase 2.4 Release | Functional Check Flight(s)
777-200 | Phase 2.4 Release | Fly Along Support
777-200 | Phase 2.4 Release | Post Implementation Follow Up
777-300 eX3 | eXTV Release | CDR / Software Req Freeze
777-300 eX3 | eXTV Release | End of Iteration Demo 1
777-300 eX3 | eXTV Release | End of Iteration Demo 2
777-300 eX3 | eXTV Release | End of Iteration Demo 3
777-300 eX3 | eXTV Release | End of Iteration Demo 4
777-300 eX3 | eXTV Release | eXTV Customer Dry Run (IFE) | 5 | 2015-06-01 | 2015-06-05
777-300 eX3 | eXTV Release | eXTV Customer Dry Run (IFC)
777-300 eX3 | eXTV Release | PAC WISP Bug Fix | 5 | 2015-06-08 | 2015-06-12
777-300 eX3 | eXTV Release | PAC WISP ALST/FE Dry Run | 5 | 2015-06-15 | 2015-06-19
777-300 eX3 | eXTV Release | Bug Fix | 5 | 2015-06-22 | 2015-06-26
777-300 eX3 | eXTV Release | FSAT/Customer ATP (IFE) | 5 | 2015-06-29 | 2015-07-03
777-300 eX3 | eXTV Release | FSAT/Customer ATP (IFC) | 15 | 2015-07-06 | 2015-07-24
777-300 eX3 | eXTV Release | SQA | 4 | 2015-08-12 | 2015-08-17
777-300 eX3 | eXTV Release | SW ODD | 1 | 2015-08-19 | 2015-08-19
777-300 eX3 | eXTV Release | SW Install
777-300 eX3 | eXTV Release | Ground Check
777-300 eX3 | eXTV Release | Functional Check Flight(s)
777-300 eX3 | eXTV Release | Fly Along Support | 5 | 2015-09-07 | 2015-09-11
777-300 eX3 | eXTV Release | Post Implementation Follow Up | 45 | 2015-11-01 | 2015-12-31